## Schedule Summary
Milestone | Schedule Date
Planned Design and Permitting Substantial Completion Date | 2025-06-01
Planned Permitting Substantial Completion Date | 2025-11-01
Planned Start Construction Date | 2025-12-01
Planned Construction Substantial Completion Date | 2026-12-31
Planned Grant Administration Substantial Completion Date | 2027-03-30

## Schedule Full
Project Schedule
# | ACTIVITY | START MONTH | DURATION (MONTHS) | END MONTH
1 | Meet with MARAD, and other Federal, State and Local Agencies and community stakeholders at the start of the process to get input on potential repair/replacement project, ensuring project process meets all applicable Federal requirements and meets any and all Federal transportation requirements. | 1 | 2 | 2
2 | Hold public involvement meetings, which will continue throughout the project. | 1 | 30 | 32
3 | Sign Contract with MARAD | 2 | 1 | 2
4 | Prepare final construction bid packages. | 2 | 2 | 4
5 | Release the construction bid package and advertise project and bid construction availability. | 4 | 2 | 5
6 | Receive bid responses. Review bid responses for inclusion of all required submission documents and requirements. Review bid responses with DOT and key stakeholders to ensure they comply with applicable Federal requirements. | 5 | 2 | 6
7 | CCHD holds public meeting; Award bid; sign contract | 6 | 1 | 6
8 | Finalize technical and engineering design of the project. | 7 | 3 | 9
9 | Finalize project costs. Review costs with MARAD. | 9 | 1 | 10
10 | Secure all state and local approvals and construction permits. | 10 | 4 | 14
11 | Construct a new dock which will withstand 50-year tsunami event tidal surges and other climate related natural hazards. Ensure all materials meet domestic preference requirements. | 15 | 12 | 26
12 | Hold pre-construction meetings and job construction meetings every two weeks and as needed during the project. | 15 | 12 | 26
13 | Install electrical, sewer, water and mechanical infrastructure to serve businesses on the dock. | 24 | 2 | 26
14 | Install new hoists to improve movement of goods in the port. | 26 | 1 | 27
15 | Perform Construction Project Close-Out Phase activities. | 27 | 3 | 30
16 | Perform PIDP Construction Grant Closeout activities. | 27 | 3 | 30

## FINAL
PIDP 2022
Expenditure Line | PIDP | CCHD Match | Total
Administrative and legal expenses | 243600 | 60900 | 304500
Architectural, engineering Permiting | 332000 | 83000 | 415000
Other architectural and engineering | 100000 | 25000 | 125000
Project inspection fees | 100000 | 25000 | 125000
Site work | 1600000 | 400000 | 2000000
Demolition and removal | 608000 | 152000 | 760000
Construction | 3177921.6 | 794480.4 | 3972402
Equipment | 244000 | 61000 | 305000
Contingencies | 961044 | 240261 | 1201305
TOTAL | 7366565.6 | 1841641.4 | 9208207
PIDP 2024
Expenditure Line | PIDP | CCHD Match | Total
Administrative and legal expenses | 202500 | 40500 | 243000
Architectural, engineering Permiting | 25000 | 25000 | 50000
Other architectural and engineering | 100000 | 25000 | 125000
Project inspection fees | 0 | 0 | 0
Site work | 0 | 0 | 0
Demolition and removal | 0 | 0 | 0
Construction | 6372500 | 1709500 | 8082000
Equipment | 800000 | 200000 | 1000000
Contingencies | 500000 |  | 500000
TOTAL | 8000000 | 2000000 | 10000000
COMBINED BUDGET
Expenditure Line | PIDP TOTAL | CCHD TOTAL | TOTAL
Administrative and legal expenses | 446100 | 101400 | 547500
Architectural and engineering | 357000 | 108000 | 465000
Other architectural and engineering | 200000 | 50000 | 250000
Project inspection fees | 100000 | 25000 | 125000
Site work | 1600000 | 400000 | 2000000
Demolition and removal | 608000 | 152000 | 760000
Construction | 9550421.6 | 2503980.4 | 12054402
Equipment | 1044000 | 261000 | 1305000
Contingencies | 1461044 | 240261 | 1701305
TOTAL | 15366565.6 | 3841641.4 | 19208207
3